Guide 2. APT Project Development

Capstone Course

1. APT Project Progress Summary

Below you will find several fields that you must complete with the requested information.

| APT Project Progress Summary | Hydra is a web and mobile system for patient monitoring and clinical follow-up, designed to support the work of family members, caregivers and healthcare professionals in supervising vital signs and coordinating care. The solution is composed of four independent microservices developed in Java with Spring Boot (authentication and user management, main CRUD, geolocation and a real-time event bridge), all backed by a PostgreSQL database hosted on Supabase; a mobile application in Angular aimed at patients and family members; a desktop application in Electron for caregivers and physicians; and an administrative web interface. The modules completed to date are: user authentication with RUT (Chilean national tax ID) validation and encryption, role and permission management, registration and consultation of patient records with Fonasa/Isapre insurance coverage, integration of ESP32 devices to capture vital signs, real-time display of heart rate and oxygen saturation, alerts for out-of-range values, profile and credential administration, clinical follow-up and coverage reports, real-time messaging between the four types of participants with file attachment support, and patient geolocation. The project is implemented and verified in its testing environment, with the main services deployed to the cloud and the source code compiling correctly across its four components. |
| --- | --- |
| Objectives | No changes were made to the objectives set out in Phase 1; they remain in force. General objective: To develop a patient monitoring and clinical follow-up system that allows family members, caregivers and healthcare professionals to supervise vital signs, the patient's location and communication with the care team, delivering timely and secure information. Specific objectives: 1. Implement a role-based authentication and authorisation mechanism, with RUT validation and protection of sensitive personal data. 2. Register and maintain the clinical records of patients, including their insurance coverage. 3. Capture and display heart rate and oxygen saturation in real time through ESP32 devices. 4. Generate timely alerts when vital signs fall outside normal physiological ranges. 5. Provide a real-time communication channel between patient, family member, caregiver and physician, with file attachment support. 6. Generate clinical follow-up and coverage reports that support decision making by the healthcare team. |
| Methodology | Together with the team, the methodology was changed to a traditional phased approach. We thoroughly reviewed the project requirements, risks, and timeline. This methodology was chosen due to the clarity of the requirements and the narrow scope given its duration of a few months. This approach allows for controlled sequential execution, facilitating phase management, efficient resource utilization, and deadline compliance, without the need for constant iterations or adjustments.: a) A microservices architecture with shared relational persistence on Supabase was adopted instead of a monolithic application, which made it possible to deploy and update each module independently. b) A real-time event bridge was introduced that translates changes produced in the database into Server-Sent Events for the web, mobile and desktop layers, replacing the periodic polling originally defined. c) Angular with TypeScript was established as the common technology for the mobile application and the web interface, and Electron for the desktop application, in order to reduce the learning curve and reuse components. d) Independent version control per microservice was adopted, with automated continuous deployments to the cloud service. e) A data protection strategy was defined that encrypts personal identifiers and messages at rest, avoiding their exposure in plain text. The architecture documentation, the use cases and the ERS proposal were prepared before development and were updated continuously as the modules were completed. |
| Progress Evidence | The evidence attached to this report is the following: 1. Source code of the four system microservices, in Java with Spring Boot, compiling without errors. 2. Package of the Android mobile application, built from the Angular project, with build identifier 92f0578a2da72e36. 3. Deployment evidence for the data management service (hydra_crud) in a production environment, with verification of its main operations: conversation retrieval (code 200), message creation (201), marking as read (200) and deletion (200), together with verification of the cross-origin (CORS) directives that permit read, create, update and delete operations. 4. System architecture diagram, showing the composition of the microservices, the shared database and the different clients (mobile application, desktop application and web interface). With regard to safeguarding project quality, the following criteria specific to the discipline were applied: verification of the compilation of each component before its delivery; smoke tests on the endpoints of each service to confirm the correct response codes; validation of the syntax of the client scripts through static analysis; comparison between the Gantt chart schedule and the effective progress, which is reflected in the Work Plan of this report; and, in terms of security, the application of encryption at rest to sensitive data (patient identifier and messages) together with an audit that identified relevant gaps, such as the exposure of cryptographic material in the mobile client, the absence of authentication on some endpoints and the storage of file attachments with public access; these gaps are included as an in-progress activity in the adjustments plan. |
| 2. Work Plan Monitoring |
| Carefully examine your work plan, focusing especially on the progress status and adjustments columns. |

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Responsible | Observations | Progress status | Adjustments |
| Project management | Project charter | Team virtual meetings | 1 week (Week 1) | Luis Aguirre (JP) | The scope, deadlines and formal structure of the project were set | Completed | No adjustments |
| Project management | Approval of the project charter | Communication with the instructor | 1 week (Weeks 1-2) | Luis Aguirre (JP) | Formal approval was obtained before starting the analysis | Completed | No adjustments |
| Requirements analysis | Definition of general requirements | Team meetings, project minutes | 1 week (Week 1) | Luis Aguirre (JP) and Francisco (DG) | The functional scope and the non-functional requirements were defined | Completed | No adjustments |
| Project management | Team organisation | Role matrix, coordination meetings | 1 week (Week 1) | Luis Aguirre (JP) | The JP/APC, DBA, QA and DG roles were assigned | Completed | No adjustments |
| Requirements analysis | Capture of specific requirements | User stories, meetings with the instructor | 1 week (Week 2) | Francisco (DG) and Luis Aguirre (JP) | Security and traceability requirements were incorporated | Completed | The backlog was extended with the traceability and access auditing requirement |
| Software design | Software architecture document | UML diagrams, architecture decisions | 1 week (Week 2) | Francisco (DG) | The interaction between the modules and with the database was documented | Completed | A microservices architecture with shared persistence was adopted instead of a monolithic application |
| Software design | Use case document | UML use case diagrams | 1 week (Week 3) | Francisco (DG) | The workflows of the four user types of the system were modelled | Completed | No adjustments |
| Interface design | Interface prototypes | Prototyping tools | 1 week (Week 3) | Francisco (DG) | The screens corresponding to the different roles were prototyped | Completed | No adjustments |
| Planning | ERS proposal | Institutional ERS template | 1 week (Week 4) | Luis Aguirre (JP) | Software requirements specification | Completed | No adjustments |
| Backend implementation | Setting up the development environment | Java 17, Spring Boot, Maven | 1 week (Week 4) | Luis Aguirre (APC) | The base projects for the services were set up | Completed | Expanded from a monolithic project into four independent microservices |
| Database administration | Creation of the database table scripts | PostgreSQL, Supabase | 2 weeks (Weeks 4-5) | Benjamin Contreras (DBA) | The entities were modelled with keys, constraints and indexes | Completed | The tables were extended to support geolocation, vital signs, history and messaging |
| Database administration | Creation of the query scripts | PostgreSQL, PostgREST | 2 weeks (Weeks 5-6) | Benjamin Contreras (DBA) | Views, functions and indexes for the reports | Completed | Composite indexes were added to speed up queries on the vital signs history |
| Backend development | Login and RUT validation module | Spring Boot, Spring Security, JWT | 1 week (Week 6) | Luis Aguirre (APC) and Benjamín Contreras (DBA) | Validation of the RUT check digit | Adjusted | The RUT is stored encrypted, with hash columns for lookups, instead of in plain text |
| Information security | Role and permission management | Spring Security, JWT | 1 week (Week 6) | Luis Aguirre (APC) | Four roles: patient, family member, caregiver and physician | Adjusted | Keys and credentials were migrated to environment variables, out of the source code |
| Backend development | Patient registration (RUT, Fonasa/Isapre) | Spring Boot, JPA, Hibernate | 1 week (Week 7) | Luis Aguirre (APC) and Benjamín Contreras (DBA) | Validation of insurance coverage and patient uniqueness | Adjusted | RUT uniqueness validation and encryption of the patient identifier were added |
| Backend development | Editing and consulting the patient record | Spring Boot, JPA | 1 week (Week 7) | Luis Aguirre (APC) | Complete management of the clinical record | Completed | No adjustments |
| Systems integration | ESP32 - Supabase integration (PostgREST) | ESP32, Wi-Fi network, REST API | 1 week (Week 8) | Luis Aguirre (APC) and Benjamin Contreras (DBA) | Continuous transmission of heart rate and oxygen saturation | Adjusted | The transmitted data set was extended with oxygen saturation and device geolocation |
| Frontend development | Real-time BPM (beats per minute) display (dashboard) | Angular, TypeScript, Server-Sent Events | 1 week (Week 9) | Francisco (DG) and Luis Aguirre (APC) | Screen refresh without manual reloading | Adjusted | Periodic polling was replaced by Server-Sent Events, which reduced latency and the load on the database |
| Systems integration | Alerts for abnormal BPM ranges | Spring Boot, threshold rules | 2 weeks (Weeks 9-10) | Luis Aguirre (APC) | Tachycardia and bradycardia thresholds | Completed | The alert was also extended to oxygen saturation |
| User administration | Manage profiles | Spring Boot, Angular | 1 week (Week 10) | Francisco (DG) | Management of contact details and preferences | Completed | No adjustments |
| Information security | Manage credentials | Spring Security, hash encoding | 1 week (Week 10) | Luis Aguirre (APC) and Benjamín Contreras (DBA) | Reset and change of access credentials | Adjusted | The reset procedure was hardened and secrets were removed from the source code |
| Frontend development | Android mobile application (patient and family member) | Angular, Capacitor, TypeScript | 3 weeks (Weeks 6-9) | Francisco (DG) | Authentication, cardiac monitoring and messaging | Adjusted | The scope was extended with the messaging screens and the use of the device camera |
| Frontend development | Desktop application (caregiver and physician) | Electron, HTML, CSS, JavaScript | 3 weeks (Weeks 8-11) | Francisco (DG) and Luis Aguirre (APC) | Staff management, monitoring and communication | Adjusted | File selection and image capture through the webcam were added |
| Backend development | Real-time messaging between the four roles | Spring Boot, SSE, Supabase Storage | 2 weeks (Weeks 8-9) | Luis Aguirre (APC) and Benjamín Contreras (DBA) | One-to-one conversations with file attachments | Adjusted | Module not included in the Gantt chart; it was added out of clinical necessity and expanded the scope of the project |
| Information security | Encryption of sensitive data and access control | Symmetric encryption, hash, HTTPS, CORS | 2 weeks (Weeks 9-10) | Luis Aguirre (APC) and Benjamín Contreras (DBA) | Encryption at rest of the patient identifier and of messages | In progress | The audit identified gaps that require authenticating the real-time channels, privatising attachment storage and removing the cryptographic material from the mobile client |
| Interface design | Administrative web interface (Hydra Web) | Angular, HTML, CSS | 2 weeks (Weeks 10-12) | Francisco (DG) | Interface for managing and consulting reports | In progress | Its integration with the new encryption strategy is still pending |
| Report development | Historical vital signs report | PostgreSQL, JPA, charts | 1 week (Week 10) | Benjamín Contreras (DBA) and Francisco (DG) | Time series of heart rate and oxygen saturation | Completed | The ability to archive old records was added |
| Report development | Patient report by insurance coverage (Fonasa/Isapre) | PostgreSQL, aggregate queries | 1 week (Week 11) | Benjamin Contreras (DBA) | Grouping by insurance system | Completed | No adjustments |
| Report development | Report export (PDF/Excel) | Document generation libraries | 1 week (Week 11) | Benjamin Contreras (DBA) | Download of the information in both formats | Completed | Scheduled report generation was added |
| Quality assurance | Setting up the testing environment | Cloud testing environment, API client | 2 weeks (Weeks 11-12) | Francisco Carrasco (QA) | A separate environment has not been required; the validation deployments are used | Not started | The construction of an isolated testing environment with anonymised data will be evaluated |
| Quality assurance | Functional tests | Test cases, endpoint tests | 2 weeks (Weeks 12-13) | Francisco Carrasco (QA) | To date, only manual smoke tests have been run against the services | Delayed | The schedule will be revised to incorporate automated tests across the four microservices |
| Quality assurance | User testing | Usage profiles, evaluation questionnaires | 2 weeks (Weeks 13-14) | Francisco Carrasco (QA) | Requires the usage profiles to be available on the deployed system | Not started | They will be scheduled once the migration to production is complete |
| Deployment | Migration of the system to production | Supabase, cloud service, SQL migrations | 1 week (Week 14) | Luis Aguirre (JP) and Benjamín Contreras (DBA) | Requires running the database migrations and configuring private storage | Not started | The encryption migrations for messages, attachments and vital signs will be run before the final release |
| Training | User training sessions | Tutorials, training meetings | 1 week (Weeks 14-15) | Luis Aguirre (JP) and Francisco (DG) | Training differentiated by user type | Not started | No adjustments |
| Documentation | User manuals | Text editor, screenshots | 1 week (Week 15) | Francisco (DG) | Manuals for patients, family members, caregivers and physicians | Not started | No adjustments |
| Project management | Project close-out document | Formal close-out document | 1 week (Week 15) | Luis Aguirre (JP) | Administrative and academic closure of the project | Not started | No adjustments |

3. Adjustments Based on Monitoring

Go deeper into the observations of your work plan. Analyse the planned activities and point out which aspects facilitated or hindered the execution of the plan. Explain how you addressed and/or will address the obstacles. Finally, indicate the adjustments you made to the work plan as a result of this analysis.

Factors that have facilitated and/or hindered the development of my work plan: The factors that facilitated the development of the work plan were the following: The organisation of the team according to clearly defined roles (Project Manager and Systems Analyst, Database Administrator, Quality and Testing, and Designer), which allowed each component of the system to have an identifiable person responsible and prevented duplicated effort. The unification of the technology stack, with Java and Spring Boot in the four microservices and Angular with TypeScript in the mobile application and the web interface, which reduced the learning curve and allowed implementation patterns to be reused across components. The use of a cloud-hosted PostgreSQL database, which removed the burden of own infrastructure and allowed the effort to be concentrated on the business logic and the data model. Independent version control per microservice, which allowed work to proceed in parallel without generating integration conflicts between features. Coordination through periodic meetings and the use of a documented technical decision log, which reduced the time lost in rebuilding the context of each task. The main factors that hindered progress were the integration between applications of different origins, in particular the access configuration between different domains; the unavailability of the free deployment service, which hibernates inactive applications and causes interruptions; the restrictions inherent to mobile development, such as obtaining camera permissions and generating the Android platform, which was not originally configured; and the absence of an independent repository for the real-time module, which makes its continuous deployment difficult.

Adjusted or Removed Activities: The activities that were adjusted or incorporated were the following: 1. Software architecture: a microservices architecture with shared persistence was adopted instead of a monolithic application, in order to allow each module to be deployed independently. 2. Database schema: it was extended to support geolocation, the recording of vital signs with oxygen saturation, the history of those signs and messaging, capabilities that were not included in the original design. 3. Login and RUT validation: the patient identifier went from being stored in plain text to being encrypted, complemented with hash columns that allow searches without exposing the data. 4. Role and credential management: all keys and credentials were migrated to environment variables, removing them from the source code. 5. ESP32 integration with Supabase: the set of transmitted data was extended, incorporating oxygen saturation and device geolocation. 6. Real-time BPM display: periodic polling of the database was replaced by an event bridge that uses Server-Sent Events, which improved update latency and reduced the load on the database server. 7. Vital signs alerts: the out-of-range alert was also extended to oxygen saturation. 8. Mobile application and desktop application: their scope was extended with the messaging screens and with the ability to attach images through file selection or camera. 9. Real-time messaging: a complete communication module between the four types of participants, with file attachments, was incorporated. It did not appear in the original Gantt chart and responds to a clinical need for coordination of the care team. 10. Reports: the ability to archive old records and scheduled report generation were added. 11. Data protection: a strategy for encrypting personal identifiers and messages at rest was defined, avoiding their exposure in plain text in the database.

Activities not started or delayed: The activities that have not been started or that are delayed are the following: 1. Setting up the testing environment (Weeks 11-12). It has not been started because until now the validation deployments have been used for smoke testing, which allowed development to proceed. The strategy to resume it is to define an isolated testing environment with anonymised data once the migration to production is complete. 2. Functional tests (Weeks 12-13). This is delayed, since to date only manual smoke tests have been run against the service endpoints, instead of a formally defined set of test cases. The strategy to overcome this is to reformulate the schedule together with the quality manager, incorporating automated tests across the four microservices and establishing acceptance criteria per module. 3. User testing (Weeks 13-14). It has not been started because it depends on the availability of the system in its final environment. It will be scheduled once the migration to production is complete, using the patient, family member, caregiver and physician profiles. 4. Migration of the system to production (Week 14). It has not been started. It requires running the outstanding database migrations for the encryption of messages and attachments, configuring private storage for the file attachments, and generating the Android platform for the mobile application. These tasks present technical risk and are considered priorities. 5. Training sessions (Weeks 14-15), User manuals (Week 15) and Project close-out document (Week 15). They have not been started because their execution presupposes the availability of the final version of the system. Their scheduling is defined according to the date of the definitive release. A common factor in these delays is the concentration of the team's effort on the development phase, which absorbed the integration between the different components of the system. We undertake the commitment to reassign part of the workload to the quality manager, so that test planning advances in parallel with the close of development.

In the case of a group APT Project, this column must state the name of those responsible for each task or activity. This will later allow the assessment of each team member to be differentiated.